## Sheet1
Group Members | Weekly Updates | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Weak 11 | Weak 12
Martin Battilana | Accomplishments | Week 1: Understood FDM printers, created a list of potential defects, created Weekly Tracking Guide; Week 2: Wrote rought draft for the executive summary, 1/3 of the problem definition and technical review and Project Objectives and quantitative goals, did research; Week 3: For proposal report: Eddited title page, improved executive summary, fixed table of contents, created formal numbering system, redid problem definition after reciving feedback, redid technical review, redid project objectives and quantitative goals to include objective, contraints and free variables, reformatted project schedule, updated and edited risk assessment, formatted technical resources, added calculations to the budget, updated safety, redid communication plan, formatted references, updated appendices. Created meeting minutes and updated them for both informal and formal meetings. Completed action items number 3, 4, 6, 7, 8, 9 and Question numbers 1,4, and 5 from Meeting Minutes for Week 3.; Week 4: Organised several team meetings to correct our lack of communication an professionalism, continued research into machine vision and vision sensors and potential methods of collecting usefull information from an optical sensor, created the outline for our Week 5 Formal Meeting Presentation, created and completed Meeting Minutes for Week 4, created and completed Week 5 Formal Agenda for the formal meeting, updated our team name on the UBC Wiki page, added relevant files to the UBC Wiki page.; Week 5: Created Outline for Midterm Presentation and completed slides for Technical Review, Design Options, and Summary and Recommendations. Created and uploaded weekly meeting minutes for week 5, created week 6 formal agenda, created and completed a simple WDM for potential design options, assigned number values to constraints, uploaded relevant files to the UBC Wiki page, researched CCD and CMOS cameras and understood the difference, learned how to do simple image processing in MATLAB; Week 6: Created Midterm Presentation File, Finished slides regarding Technical Review, Design Options, and Recommendations, upon presenting to Chad in formal meeting, had to redo slides in the Midterm Presentation, edited slides regarding introduction, problem defintion, and specification definition, practiced Miterm Presentation, Research various vision, thermal, and laser line sensors including shearography, and 3D scanning, Filled out several Parts of Midterm Report including: executive summary, technical review, project objective and quantitative goals, redid section on economic assesment of design, edited sections: design options using vision sensors, design options using thermal sensors, design options using laser-based sensors, laser line profile sensor, 3D scanner, laser shearography, design recommendations, updated project schedule, risk assessment, references, appendicies, table of contents, edited whole report for grammar and flow. Also created meeting mintues for Week 6 and Week 7 Formal Meeting Agenda, and uploaded relevant files to the UBC Wiki page.
| Blockers | Week 1: Nothing; Week 2: Communication/Project progression in order to respond to Chad's emails; Week 3: Getting access to the 3D printer and visualizing potential solutions; Week 4: None; Week 5: Research results from other group members; Week 6: Nothing
| Goals For Next Week | Week 1: Work on proposal report, do more research, come up with some potential Ideas; Week 2: Finalize my part for the Proposal Report, Proof read all parts and fix/edit grammatical error with report; Week 3: Continue research into machine vision and vision sensors.; Week 4: Set up Midterm Report and start working on a rought draft of the Midterm Report; Week 5: Refine and practice Midterm Presentation, Complete rough draft from Midterm Report and then finalize the Midterm Report, figure out how to get a reference image of the printed part to compare the processed image to, reformat the Wiki Page to make it more readable; Week 6: Discuss project progression and the next steps moving forward
| Time Spent On Project This Week | Week 1: 5 hours; Week 2: 6 hours; Week 3: 28 hours; Week 4: 8 hours; Week 5: 16 hours; Week 6: 60 hours
Jacob Koo | Accomplishments | Week 1: Research on FDM product defects, types and certain methods used to identify said defects.
| Blockers | Week 1: FDM Printer access
| Goals For Next Week | Week 1: Problem definition, Identify constraints, free variables etc. Get access to FDM printer, identify available tech (sensors, CPUs etc.)
| Time Spent On Project This Week | Week 1: 2.5 hours
Hin Yao Chow | Accomplishments | Week 2: Research FDM 3D Printing, and common defects, Set up Gannt Chart; Week 3: Prepared Gantt Chart, Worked on Project Proposal Report. Review Defects in detail; Week 4: Learned about laser traingulation, suggested method of using ciclop 3D scanners as an error detection method; Week 5: Worked on Midterm Presentation. Review Feedback Procedure. Refine Problem definition. Define Unrecoverable modelling in terms of defects.; Week 6: Midterm Presentation, midterm report.
| Blockers | Week 2: None; Week 3: None; Week 4: Ciclop 3D scanner does not have highly posistive ratings. Other 3D scanners a little too expensive; Week 5: None; Week 6: none
| Goals For Next Week | Week 2: Begin Drafting Proposal Report, have problem definitions and overview spot on; Week 3: FinishingProject Proposal and have a solid Problem Definition; Week 4: Look alternative photo of error detection with just camera; Week 5: Create Feedback Flowchart through layer by layer scanning; Week 6: final design illustration and feedback loop flowchart
| Time Spent On Project This Week | Week 2: 4 hr; Week 3: 4 hr; Week 4: 6 hours; Week 5: 8 hours; Week 6: 8 hr
Kevin Zhu | Accomplishments | Week 2: Resaerch on types of FDM printing failures, (which ones have the highest chance of failing ); Week 3: Research on possible risks for a engineering project, worked on the risk assessment and have it revised after formal meeting with sponsor; Week 4: Researching on the principle of line laser defect detection as well as detecting speed and resolution.; Week 5: Research on the line laser scanning system on the aspect of data obtaining and experimental data&scholars. Also did research on the price of ccd camera regarding different resolutions; Week 6: Continue on research on the line laser detection method and figure out the quantitative measurement of the defects. Working on the design option part for the midterm report
| Blockers | Week 2: None; Week 3: None; Week 4: None; Week 5: None; Week 6: None
| Goals For Next Week | Week 2: Have access to the specific FDM printer to see the potential aspects of failing beside the general ones; Week 3: Finishing Project proposal and have a deeper understanding of the potential risks during the project and solutions to them; Week 4: Discuss the method with team members and find the most optimal combination of laser projector and sensoring camera according to budget and necessary sensitivity to defects; Week 5: Start working on midterm report. Continue searching related scholars; Week 6: Optimize the design details
| Time Spent On Project This Week | Week 2: 3.5hrs; Week 3: 5hrs; Week 4: 6.5hrs; Week 5: 8 hours; Week 6: 10 hours
Oliver Tian | Accomplishments | Week 1: Learn the basics of Additive manufacturing and FDM printing; Week 2: Reasearch on FDM printing materials and modes of failures; Week 3: Make a table for the initial project schedule in the proposal, also do the research on and find out a previous inappropriate solution for the technical review part; Week 4: Researching on the speckle pattern resolution enhancement, read several articles about this topic and find out the processing data and specifications for its implementation; Week 5: Doing research on the speckle pattern scanning on the aspect of the specifications opf the device, the price for parts and the general working principal of it. Additionally, doing research on image processing; Week 6: Doing research on CCD and CMOS vision sensors and the way of processing the data on matlab and working on the 'design option' part for midterm report
| Blockers | Week 1: None; Week 2: None; Week 3: None; Week 4: None; Week 5: None; Week 6: None
| Goals For Next Week | Week 1: Do more research on the FDM printing; Week 2: Commencing the delegated part of Drafting Proposal Report and do more investigations and give constructive ideas; Week 3: Did more research on the common defects during FDM printing; Week 4: Discuss the speckle method with teammates and Project Leader and reach the consensus of the viable ways of detection; Week 6: Try to find more quantitative assessment of using the vision sensor
| Time Spent On Project This Week | Week 1: 2 hours; Week 2: 3 hr; Week 3: 5 hours; Week 4: 7 hours; Week 5: 10 hours; Week 6: 12 hours
Devang Lamba | Accomplishments | Week 1: Understood Project and its deliverables, Met with team members and organized communication; Week 2: Reasearch of FDM material failure,printing process, types of materials available and growth of additive manufacturing; Week 3: Worked on Project proposal Budgeting, Safety and Resources, editing and clarifying sections to be concise, Researched on types of sensors such as LIDAR; Week 4: Research in operating a 3D printer, review of team reasearch and support in reasearch for image proccessing,; Week 5: Underwent Training for 3D printers, researched on Camera and laser setups, Understanding of causes of defects by printing parameters and assigning of research roles and collecting information from each member; Week 6: Working on the Midterm report and feedback for the midterm presentations
| Blockers | Week 1: None; Week 2: Access to the FDM printer and training for it; Week 3: None; Week 4: No access to training; Week 5: Sick from viral Flu for 3 days; Week 6: None
| Goals For Next Week | Week 1: Begin Researching the project; Week 2: Work on proposal and research existing methods to correct it; Week 3: Investigating further on sensors and finishing report; Week 4: zoning into one method to use and obtaining working concept; Week 5: Research on machine learning technology and the development of near failure models to test setup on detection; Week 6: Quantitative analysis via feedback from the presentation, group organisation
| Time Spent On Project This Week | Week 1: 2.5 hours; Week 2: 4 hrs; Week 3: 5 hours; Week 4: 4 hours; Week 5: 6 hours; Week 6: 10 Hours
Additional Questions
Comments |  | Week 2: Jacob Koo has failed to fill out his status.; Week 3: Jacob Koo has failed to fill out his status.; Week 4: Jacob Koo has failed to fill out his status.; Week 5: Jacob Koo has failed to fill out his status.; Week 6: Jacob Koo has failed to fill out his status.