## Sheet2
| MTRL 466: Adaptive Architecture |  |  |  | Vicki Pistner
Lauren Day
Jeremy Leung
Kush Shah
Ted Hung
Juan Ellorin
Group
Task |  | Allotted Days | September | [21 empty] | October | [30 empty] | November
|  |  | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday
|  |  | 9th | 10th | 11th | 12th | 13th | 14th | 15th | 16th | 17th | 18th | 19th | 20th | 21st | 22nd | 23rd | 24th | 25th | 26th | 27th | 28th | 29th | 30th | 1st | 2nd | 3rd | 4th | 5th | 6th | 7th | 8th | 9th | 10th | 11th | 12th | 13th | 14th | 15th | 16th | 17th | 18th | 19th | 20th | 21st | 22nd | 23rd | 24th | 25th | 26th | 27th | 28th | 29th | 30th | 31st | 1st | 2nd | 3rd | 4th | 5th | 6th | 7th | 8th | 9th | 10th | 11th | 12th | 13th | 14th | 15th | 16th | 17th | 18th | 19th | 20th | 21st | 22nd | 23rd | 24th | 25th | 26th | 27th | 28th | 29th | 30th
Project Timeline
Compile Questions for Blaire | bar: 9th to 11th
Create Preliminary Gantt Chart of Timeline | bar: 9th to 13th
Define Project Objectives | bar: 9th to 13th
Develop an Engineering Critique | bar: 9th to 13th
Initial Literary Review
Bimaterials | bar: 9th to 20th
Shape Memory Materials | bar: 9th to 20th
Thermal Analysis
Austin Seasonal Temperature Data | bar: 9th to 13th
Building Interior Temperature Calculations | bar: 9th to 22nd
Life Cycle Analysis
Learn program/practice with potential materials | bar: 13th to 20th
Examine frame and hinge material options | bar: 28th to 4th
Cost Analysis
Concept
Determine Functional Structure | bar: 14th to 20th
Seek Working Principles
BiMaterial | bar: 14th to 20th
Finalise bimaterial parameters | bar: 21st to 27th
Determine feasibility of bimaterial | bar: 14th to 27th
ShapeMemory | bar: 14th to 20th
Finalise shape memory parameters | bar: 21st to 27th
Determine feasibility of shape memory | bar: 14th to 27th
Evaluate and Select Concepts | bar: 28th to 11th
Embodiment
Develop Layout, Concept, Form | bar: 9th to 20th
Finalise frame design | bar: 12th to 18th
Choose bimaterial | bar: 28th to 11th
Choose shape memory material | bar: 28th to 11th
Model and Analyse Assemblies | bar: 5th to 18th; 26th to 1st
Evaluate and Select Layouts | bar: 26th to 1st
Detail
Analyse Components | bar: 2nd to 8th
Optimize Performance and Cost | bar: 9th to 15th
Final choice of Material and Process | bar: 16th to 22nd
Midterm Presentation & Report
Written Sections |  |  | 9th: Started. Will add
| Needs and Constraints |  | 9th: Started. Will add
Problem Specification | bar: 28th to 11th
Technical Review | bar: 28th to 11th
Assess and Select Design Options | bar: 28th to 11th
Team Responsibilities | bar: 28th to 11th
Final Presentation & Report
Written Sections
Executive Summary | bar: 16th to 29th
Needs and Constraints | bar: 16th to 29th
Problem Specification | bar: 16th to 29th
Technical Review | bar: 16th to 29th
Assess and Select Design Options | bar: 16th to 29th
Detailed Design | bar: 16th to 29th
Socio-Economic Assessment of Design | bar: 16th to 29th
Recommendations | bar: 16th to 29th
Team Responsibilities | bar: 16th to 29th