## Sheet1
|  | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12 | Week 13
Tasks | Roles | Sept 8 - 14 | Sept 15 - 21 | Sept 22 - 28 | Sept 29- Oct 5 | Oct 6 - 12 | Oct 13 - 19 | Oct 20- 26 | Oct 27 - Nov 2 | Nov 3 - 9 | Nov 10 - 16 | Nov 17 - 23 | Nov 24 - 30
Tasks Identification and Planning | bar: Week 2
Problem Identification | bar: Week 2
Design Objectives | bar: Week 3
Identify Project Risks | bar: Week 3
Budget Scoping | bar: Week 3
Identify Safety Hazards | bar: Week 3
Proposal Due
Review Project Proposal Feedback | bar: Week 3 to Week 4
Technical Research for Solutions | bar: Week 4
Design Brainstorming (3/4 Designs) | bar: Week 4 to Week 5
Design Options (Narrow to 2?) | bar: Week 4 to Week 5
Select Final Design | bar: Week 6
Project Risk Assement Update | bar: Week 6
Discuss Economic / Socio-Economic & LCA | bar: Week 6
Project Presentation & Report Preparation | bar: Week 6
Midterm Report Due
Midterm Presentation
Review Midterm Report Feedback | bar: Week 7 to Week 8
Iterate Final Design | bar: Week 8 to Week 9
Improve Economic / Socio-Economic & LCA | bar: Week 8 to Week 9
Illustrate Working Principle (Quantitative) | bar: Week 8 to Week 10
Calculations | bar: Week 8 to Week 10
Rapid Prototyping | bar: Week 8 to Week 10
Final Report Prepartion | bar: Week 11 to Week 12
Final Report Due
Final Presentation