## Sheet1
Group Members | Weekly Updates | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Weak 11 | Weak 12
Martin Battilana | Accomplishments | Week 1: Understood FDM printers, created a list of potential defects, created Weekly Tracking Guide; Week 2: Wrote rought draft for the executive summary, 1/3 of the problem definition and technical review and Project Objectives and quantitative goals, did research; Week 3: For proposal report: Eddited title page, improved executive summary, fixed table of contents, created formal numbering system, redid problem definition after reciving feedback, redid technical review, redid project objectives and quantitative goals to include objective, contraints and free variables, reformatted project schedule, updated and edited risk assessment, formatted technical resources, added calculations to the budget, updated safety, redid communication plan, formatted references, updated appendices. Created meeting minutes and updated them for both informal and formal meetings. Completed action items number 3, 4, 6, 7, 8, 9 and Question numbers 1,4, and 5 from Meeting Minutes for Week 3.
| Blockers | Week 1: Nothing; Week 2: Communication/Project progression in order to respond to Chad's emails; Week 3: Getting access to the 3D printer and visualizing potential solutions
| Goals For Next Week | Week 1: Work on proposal report, do more research, come up with some potential Ideas; Week 2: Finalize my part for the Proposal Report, Proof read all parts and fix/edit grammatical error with report; Week 3: Continue research into machine vision and vision sensors.
| Time Spent On Project This Week | Week 1: 5 hours; Week 2: 6 hours; Week 3: 28 hours
Jacob Koo | Accomplishments | Week 1: Research on FDM product defects, types and certain methods used to identify said defects.
| Blockers | Week 1: FDM Printer access
| Goals For Next Week | Week 1: Problem definition, Identify constraints, free variables etc. Get access to FDM printer, identify available tech (sensors, CPUs etc.)
| Time Spent On Project This Week | Week 1: 2.5 hours
Hin Yao Chow | Accomplishments | Week 2: Research FDM 3D Printing, and common defects, Set up Gannt Chart; Week 3: Prepared Gantt Chart, Worked on Project Proposal Report. Review Defects in detail
| Blockers | Week 2: None; Week 3: None
| Goals For Next Week | Week 2: Begin Drafting Proposal Report, have problem definitions and overview spot on; Week 3: FinishingProject Proposal and have a solid Problem Definition
| Time Spent On Project This Week | Week 2: 4 hr; Week 3: 4 hr
Kevin Zhu | Accomplishments | Week 2: Resaerch on types of FDM printing failures, (which ones have the highest chance of failing ); Week 3: Research on possible risks for a engineering project, worked on the risk assessment and have it revised after formal meeting with sponsor
| Blockers | Week 2: None; Week 3: None
| Goals For Next Week | Week 2: Have access to the specific FDM printer to see the potential aspects of failing beside the general ones; Week 3: Finishing Project proposal and have a deeper understanding of the potential risks during the project and solutions to them
| Time Spent On Project This Week | Week 2: 3.5hrs; Week 3: 5hrs
Oliver Tian | Accomplishments | Week 2: Reasearch on FDM printing materials and modes of failures; Week 3: Make a table for the initial project schedule in the proposal, also do the research on and find out a previous inappropriate solution for the technical review part
| Blockers | Week 2: None; Week 3: Did more research on the common defects during FDM printing
| Goals For Next Week | Week 2: Commencing the delegated part of Drafting Proposal Report and do more investigations and give constructive ideas
| Time Spent On Project This Week | Week 2: 3 hr; Week 3: 5 hours
Devang Lamba | Accomplishments | Week 1: Understood Project and its deliverables, Met with team members and organized communication; Week 2: Reasearch of FDM material failure,printing process, types of materials available and growth of additive manufacturing; Week 3: Worked on Project proposal Budgeting, Safety and Resources, editing and clarifying sections to be concise, Researched on types of sensors such as LIDAR
| Blockers | Week 1: None; Week 2: Access to the FDM printer and training for it; Week 3: None
| Goals For Next Week | Week 1: Begin Researching the project; Week 2: Work on proposal and research existing methods to correct it; Week 3: Investigating further on sensors and finishing report
| Time Spent On Project This Week | Week 1: 2.5 hours; Week 2: 4 hrs; Week 3: 5 hours
Additional Questions
Comments |  | Week 2: Jacob Koo has failed to fill out his status.; Week 3: Jacob Koo has failed to fill out his status.