## Sheet1
Group Members | Weekly Updates | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Weak 11 | Weak 12
Martin Battilana | Accomplishments | Week 1: Understood FDM printers, created a list of potential defects, created Weekly Tracking Guide; Week 2: Wrote rought draft for the executive summary, 1/3 of the problem definition and technical review and Project Objectives and quantitative goals, did research; Week 3: For proposal report: Eddited title page, improved executive summary, fixed table of contents, created formal numbering system, redid problem definition after reciving feedback, redid technical review, redid project objectives and quantitative goals to include objective, contraints and free variables, reformatted project schedule, updated and edited risk assessment, formatted technical resources, added calculations to the budget, updated safety, redid communication plan, formatted references, updated appendices. Created meeting minutes and updated them for both informal and formal meetings. Completed action items number 3, 4, 6, 7, 8, 9 and Question numbers 1,4, and 5 from Meeting Minutes for Week 3.; Week 4: Organised several team meetings to correct our lack of communication an professionalism, continued research into machine vision and vision sensors and potential methods of collecting usefull information from an optical sensor, created the outline for our Week 5 Formal Meeting Presentation, created and completed Meeting Minutes for Week 4, created and completed Week 5 Formal Agenda for the formal meeting, updated our team name on the UBC Wiki page, added relevant files to the UBC Wiki page.
| Blockers | Week 1: Nothing; Week 2: Communication/Project progression in order to respond to Chad's emails; Week 3: Getting access to the 3D printer and visualizing potential solutions; Week 4: None
| Goals For Next Week | Week 1: Work on proposal report, do more research, come up with some potential Ideas; Week 2: Finalize my part for the Proposal Report, Proof read all parts and fix/edit grammatical error with report; Week 3: Continue research into machine vision and vision sensors.; Week 4: Set up Midterm Report and start working on a rought draft of the Midterm Report
| Time Spent On Project This Week | Week 1: 5 hours; Week 2: 6 hours; Week 3: 28 hours; Week 4: 8 hours
Jacob Koo | Accomplishments | Week 1: Research on FDM product defects, types and certain methods used to identify said defects.
| Blockers | Week 1: FDM Printer access
| Goals For Next Week | Week 1: Problem definition, Identify constraints, free variables etc. Get access to FDM printer, identify available tech (sensors, CPUs etc.)
| Time Spent On Project This Week | Week 1: 2.5 hours
Hin Yao Chow | Accomplishments | Week 2: Research FDM 3D Printing, and common defects, Set up Gannt Chart; Week 3: Prepared Gantt Chart, Worked on Project Proposal Report. Review Defects in detail; Week 4: Learned about laser traingulation, suggested method of using ciclop 3D scanners as an error detection method
| Blockers | Week 2: None; Week 3: None; Week 4: Ciclop 3D scanner does not have highly posistive ratings. Other 3D scanners a little too expensive
| Goals For Next Week | Week 2: Begin Drafting Proposal Report, have problem definitions and overview spot on; Week 3: FinishingProject Proposal and have a solid Problem Definition; Week 4: Look alternative photo of error detection with just camera
| Time Spent On Project This Week | Week 2: 4 hr; Week 3: 4 hr; Week 4: 6 hours
Kevin Zhu | Accomplishments | Week 2: Resaerch on types of FDM printing failures, (which ones have the highest chance of failing ); Week 3: Research on possible risks for a engineering project, worked on the risk assessment and have it revised after formal meeting with sponsor; Week 4: Researching on the principle of line laser defect detection as well as detecting speed and resolution.
| Blockers | Week 2: None; Week 3: None; Week 4: None
| Goals For Next Week | Week 2: Have access to the specific FDM printer to see the potential aspects of failing beside the general ones; Week 3: Finishing Project proposal and have a deeper understanding of the potential risks during the project and solutions to them; Week 4: Discuss the method with team members and find the most optimal combination of laser projector and sensoring camera according to budget and necessary sensitivity to defects
| Time Spent On Project This Week | Week 2: 3.5hrs; Week 3: 5hrs; Week 4: 6.5hrs
Oliver Tian | Accomplishments | Week 1: Learn the basics of Additive manufacturing and FDM printing; Week 2: Reasearch on FDM printing materials and modes of failures; Week 3: Make a table for the initial project schedule in the proposal, also do the research on and find out a previous inappropriate solution for the technical review part; Week 4: Researching on the speckle pattern resolution enhancement, read several articles about this topic and find out the processing data and specifications for its implementation
| Blockers | Week 1: None; Week 2: None; Week 3: None; Week 4: None
| Goals For Next Week | Week 1: Do more research on the FDM printing; Week 2: Commencing the delegated part of Drafting Proposal Report and do more investigations and give constructive ideas; Week 3: Did more research on the common defects during FDM printing; Week 4: Discuss the speckle method with teammates and Project Leader and reach the consensus of the viable ways of detection
| Time Spent On Project This Week | Week 1: 2 hours; Week 2: 3 hr; Week 3: 5 hours; Week 4: 7 hours
Devang Lamba | Accomplishments | Week 1: Understood Project and its deliverables, Met with team members and organized communication; Week 2: Reasearch of FDM material failure,printing process, types of materials available and growth of additive manufacturing; Week 3: Worked on Project proposal Budgeting, Safety and Resources, editing and clarifying sections to be concise, Researched on types of sensors such as LIDAR; Week 4: Research in operating a 3D printer, review of team reasearch and support in reasearch for image proccessing,
| Blockers | Week 1: None; Week 2: Access to the FDM printer and training for it; Week 3: None; Week 4: No access to training
| Goals For Next Week | Week 1: Begin Researching the project; Week 2: Work on proposal and research existing methods to correct it; Week 3: Investigating further on sensors and finishing report; Week 4: zoning into one method to use and obtaining working concept
| Time Spent On Project This Week | Week 1: 2.5 hours; Week 2: 4 hrs; Week 3: 5 hours; Week 4: 4 hours
Additional Questions
Comments |  | Week 2: Jacob Koo has failed to fill out his status.; Week 3: Jacob Koo has failed to fill out his status.; Week 4: Jacob Koo has failed to fill out his status.