## Group 1 - Gantt
Process Modelling for Adhesive Bonding of Aluminum Automotive Sheet | [8 empty] | Project Members: |  |  | Jerry Chang, Michael Fu, Judy Makmillen, Adam Ohashi
MTRL 466 - Group 1 | [8 empty] | Start Date: |  |  | 2011-09-09
| Jerry | [7 empty] | End Date: |  |  | 2011-10-17
Judy
Mike
Adam
| All |  | September | [21 empty] | October
[42] |  |  | 9th | 10th | 11th | 12th | 13th | 14th | 15th | 16th | 17th | 18th | 19th | 20th | 21st | 22nd | 23rd | 24th | 25th | 26th | 27th | 28th | 29th | 30th | 1st | 2nd | 3rd | 4th | 5th | 6th | 7th | 8th | 9th | 10th | 11th | 12th | 13th | 14th | 15th | 16th | 17th
| Task | Duration (Days) | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday
1 | Project Timeline
1.1 | Develop project timeline to midterm | 8 | bar: September 9th to September 16th
1.2 | Create Gantt chart from timeline | 8 | bar: September 9th to September 16th
1.3 | Review and define project objectives | 8 | bar: September 9th to September 16th
2 | Literature Review
2.1 | Adhesive Bonding | 5 | bar: September 12th to September 16th
2.2 | Aluminum Alloys in Automobiles | 5 | bar: September 12th to September 16th
2.3 | Aluminum Alloy Review | 5 | bar: September 12th to September 16th
2.4 | Paint Bake Cycle | 5 | bar: September 12th to September 16th
3 | Process Modelling
3.1 | Literature review of Heat Transfer Model | 6 | bar: September 17th to September 22nd
3.2 | Literature review of Mechanical Properties Model | 6 | bar: September 17th to September 22nd
3.3 | Literature review of Adhesive Curing Model | 6 | bar: September 17th to September 22nd
3.2 | Begin implementing models | 19 | bar: September 19th to October 7th
3.3 | Model validation | 19 | bar: September 19th to October 7th
4 | Midterm Presentation & Report
4.1 | Build midterm presentation | 11 | bar: October 4th to October 14th
4.2 | Build midterm report | 7 | bar: October 11th to October 17th